## Task_Log
Task ID | Lifecycle Phase | Task Description | Dependencies | Target Schedule | Actual Date | Performance Status | Verification Gate / Output Metric
WP-2.1 | Scope & Design | Freeze SRS Architecture & Two-Pass Matrix Logic formulas. | None | Day 1 (AM) | 2026-07-14 | Complete | Matrix equations committed to design repository.
WP-2.2 | Environment Setup | Generate application scaffolding inside bolt.new using specialized prompt parameters. | WP-2.1 | Day 1 (PM) | Pending | Complete | Sandbox preview active with zero loop errors.
WP-2.3 | Package Extraction | Download project payload ZIP and extract into an isolated local directory (...\baking-hydration-calculator\). | WP-2.2 | Day 2 (AM) | Pending | Complete | tsconfig.json boundary restricted; no parent path traversal.
WP-2.4 | QA & UAT | Execute functional logic tests against direct mass inputs and proportional back-calculations. | WP-2.3 | Day 2 (PM) | Pending | Complete | Zero cumulative rounding drift verified across a 10kg batch.
WP-2.5 | Production Deploy | Push the self-contained build folder payload to Netlify Drop under dedicated serverless domain mapping. | WP-2.4 | Day 3 (AM) | Pending | In Progress | Production edge deployment returns a Site is live ✨ status token.
|  | Infrastructure Rationalization – Decommission manual deployment (Project 1) and centralize subdomain management under the GitHub-linked production site (Project 2) to ensure a single source of truth for all utility deployments. |  |  |  | Not Started
|  | Environment Consolidation – Remove custom domain association from the duplicate manual project sensational-jalebi-dcf6d5, decommission the duplicate instance, and bind the active baking.headsup-consulting.com subdomain to your clean, GitHub-linked baking-hydration-calculator project. |  |  |  | Complete
Execute Project Phase: CI/CD Pipeline Integration – Decommission the legacy manual deployment of spacing-calculator, establish the GitHub-to-Netlify build pipeline for jamespnz/spacing-calculator, and assign spacing.headsup-consulting.com as the primary secure production domain.
Update the configuration management baseline by saving the high-trust strategic instructions to the user profile memory, officially incorporating the new operational principles into the system development life cycle. Language Style: PMI PMBOK Guide 7th Edition metrics.
WP-2.6 | Telemetry Ingest | Establish URL-prefix property mapping in GSC and drop the HTML verification asset into the deployment folder root. | WP-2.5 | Day 3 (PM) | Pending | Not Started | Endpoint path clears 404 error; GSC ownership confirmed.
WP-2.7 | Phase Closeout | Initialize Day 1 log entry in the GSC Telemetry Log workbook to trigger the 7-day observation track. | WP-2.6 | Day 4 (AM) | Pending | Not Started | Sprint deliverables archived; master project Gantt updated.

## artifacts
Item | URL
github repo URL | https://github.com/jamespnz/baking-hydration-calculator.git

## Sheet1
Record Type | Host / Name | Value / Points To | TTL
CNAME | baking | Your-unique-netlify-app-name.netlify.app | Automatic or 3600

## SRS_freeze_notice
1. System Requirements Specification (SRS) Freeze Notice
Project Title: The Baker's Scaling & Hydration Engine Micro-Utility
Status: ARCHITECTURE FROZEN
Framework Alignment: PMI PMBOK Guide 7th Edition (Quality & Delivery Performance Domains)
This document locks the structural, mathematical, and state boundaries for the upcoming weekend development sprint. Any changes to this architecture post-freeze will require a formal variance request to protect the deployment schedule.
2. Stateful System Architecture & Lifecycle Boundaries
To enforce the required stateful automation principles, the system eliminates reliance on runtime memory, user intent, or luck by adhering to a strict, immutable lifecycle loop.
Explicit State Tracking: The system makes its input variables, processing time, user identity tokens, and scaling intent fully transparent by caching them directly in local browser memory.
Safe-by-Design Execution: Calculation loops run as pure, unmutated functions. The user interface defaults to a real-time Preview State; no independent side effects (such as updating local storage or triggering print layouts) are executed without explicit confirmation. Reruns, parameter changes, and clear functions are safe by design.
3. Two-Pass Mathematical Matrix Blueprint
The calculation engine uses a two-pass matrix to process weights down to the single gram, completely neutralizing cumulative rounding drift over large-volume commercial production runs.
Variable Matrix Definitions
Let:
$M_{\text{flour}}$ be the absolute calculated or input mass of total flour (the $100\%$ anchor state).
$P_i$ be the explicit Baker's Percentage assigned to ingredient $i$.
$M_i$ be the calculated absolute target mass for ingredient $i$.
$Y_{\text{target}}$ be the total target batch yield mass input by the baker.
Pass 1: Total Percentage Summation
The engine aggregates all individual recipe percentage components relative to the total flour base ($100\%$):
$$P_{\text{total}} = 100 + P_{\text{hydration}} + \sum_{i=1}^{n} P_i$$
Pass 2: Mass Isolation Loop
Depending on the user's selected input driver, the engine evaluates one of two deterministic pathways:
Pathway A: Driven by Flour Mass (Direct Scaling)
If the total flour weight is explicitly entered by the user, the individual ingredient masses are resolved directly:
$$M_i = \frac{M_{\text{flour}} \times P_i}{100}$$
Pathway B: Driven by Target Yield Mass (Proportional Back-Calculation)
If a total target yield is requested, the system isolates the hidden flour anchor mass first, ensuring the system state remains visible and verifiable:
$$M_{\text{flour}} = \frac{Y_{\text{target}}}{P_{\text{total}}} \times 100$$
Once $M_{\text{flour}}$ is established, the engine loops back through the array ledger to calculate every individual ingredient mass ($M_i$) using the Pathway A formula, completely zeroing out tracking variance across the batch.